## Team and Project Details
Team Name: Avengers
Team Members: Sumanth Ravipati Shilpi Kumari Zankhna Randeri Harshit Nagpal
Link to our team's GitHub Repo: | https://github.com/sumanthravipati/Avengers_Starbucks
Link to our team's Project Board | Project Board
Link to our team's Project Journal | Weekly Status Report
XP Core Values
Link to our team's Google Sprint Task Sheet | Google Sprint Task Sheet
GitHub Contribution | GitHub Contribution
Team Members | Areas of contributions
Shilpi | 1. Payment API - Implement a REST API on top of the Starbucks Library to enable Payments 2. Weekly Status Reports 3. Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer
Zankhna | 1. Managed Order API - Implement a REST API on top of the Starbucks Library to Manage Orders 2. Architecture Diagram 3. Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer
harshit | 1. Login and Sign Up 2. Project Demo Presentation 3. Deploy API to AWS as Docker Containers in Amazon Containers
Sumanth | 1. Add Cards API - Implement a REST API on top of the Starbucks Library to enable Adding Cards 2. Burndown Chart 3. Deploy API to AWS as Docker Containers in Amazon Containers

## Google Sprint Task Sheet
|  |  |  | Week #1 (14 hrs / week) | [6 empty] | Week #2 (14 hrs / week) | [6 empty] | Week #3 (14 hrs / week)
|  |  | Initial Estimate (Total Sprint Hours = 32 x 4) | D1D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16
|  |  |  | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09
Backlog Item | Task | Task Owner | Initial Estimates | 2019-04-24: 160
|  |  | 128 | 2019-04-24: 160
Create Github Project Repo for team | Create Github Project Repo for team and provide access to team members | Sumanth Ravipati | 1 | 0 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Application Design | Design Business Logic | Zankhna Randeri | 3 | 2 | 1 | 0 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
|  | Harshit Nagpal | 3 | 2 | 1 | 0 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
| Analysing the optimal design patten for problem statement | Sumanth Ravipati | 3 | 2 | 1 | 0 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
|  | Shilpi Kumari | 3 | 2 | 1 | 0 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Implement APIs | Add Cards API - Implement a REST API on top of the Starbucks Library to enable Adding Cards | Sumanth Ravipati | 20 | 20 | 20 | 20 | 18 | 16 | 15 | 12 | 10 | 8 | 5 | 4 | 2 | 0 |  | _ | _
| Managed Order API - Implement a REST API on top of the Starbucks Library to Manage Orders | Zankhna Randeri | 20 | 20 | 20 | 20 | 19 | 17 | 15 | 13 | 11 | 9 | 7 | 4 | 3 | 0 |  | _ | _
| Payment API - Implement a REST API on top of the Starbucks Library to enable Payments | Shilpi Kumari | 20 | 20 | 20 | 20 | 17 | 16 | 13 | 12 | 10 | 7 | 5 | 3 | 2 | 0 |  | _ | _
| Other APIs - Login and Sign Up | Harshit Nagpal | 20 | 20 | 20 | 20 | 19 | 16 | 14 | 11 | 10 | 8 | 6 | 4 | 1 | 0 |  | _ | _
Complete Unit Testing | Do unit testing for all the APIs | Shilpi Kumari | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | _ | _
|  | Harshit Nagpal | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Test all the APIs together | Test all the APIs together | Zankhna Randeri | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | _
|  | Sumanth Ravipati | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | _
Deploy APIs on AWS cloud using EC2, Load Balancer and Docker Container | Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer | Shilpi Kumari | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | _
|  | Zankhna Randeri | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | _
| Deploy API to AWS as Docker Containers in Amazon Containers | Sumanth Ravipati | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  | Harshit Nagpal | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Write Documentation | Architecture Diagram | Zankhna Randeri | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Weekly Status Report | Shilpi Kumari | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0
| Project Demo Presentation | Harshit Nagpal | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Burndown Chart | Sumanth Ravipati | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
135
|  |  | Remaining Hrs (Total) | 121 | 117 | 113 | 106 | 98 | 90 | 79 | 72 | 63 | 54 | 46 | 39 | 31 | 21 | 9 | 0
Team:
Shilpi Kumari | 14 hours / Week
Zankhna Randeri | 14 hours / Week
Harshit Nagpal | 14 hours / Week
Sumanth Ravipati | 14 hours / Week
Total Available Hours During Sprint: | 128
Burndown Chart
Days | Hours of Work Remaining | Estimated hours
Day 1 | 121 | 135
Day 2 | 117 | 126
Day 3 | 113 | 117
Day 4 | 106 | 108
Day 5 | 104 | 99
Day 6 | 100 | 90
Day 7 | 79 | 81
Day 8 | 72 | 72
Day 9 | 63 | 63
Day 10 | 54 | 54
Day 11 | 46 | 45
Day 12 | 39 | 36
Day 13 | 31 | 27
Day 14 | 21 | 18
Day 15 | 13 | 9
Day 16 | 0 | 0

## Story Board Tracker
Icebox: Stories which are confirmed and yet to start
Current Iteration/Backlog: Current week user stories and their progress
Done: Completed stories

## Weekly Status Report
WEEKLY STATUS REPORT
| Dates | Days |  | Harshit | Shilpi | Zankhna | Sumanth
Week #1 (14 hrs / week) | 2019-04-24 | Day 1 | Completed | Keep-off meeting to discuss the project. And created the GitHub Repo and access to team meambers.
|  |  | Planning for next day | Work on designing business logic | work on Analysing the optimal design patten for problem statement | work on designing business logic | work on Analysing the optimal design patten for problem statement
|  |  | Blockers | None
| 2019-04-25 | Day 2 | Completed | Continue working on designing of business logic | Continue working on Analysing the optimal design patten for problem statement | Continue working on designing of business logic | Continue working on Analysing the optimal design patten for problem statement
|  |  | Planning for next day | Complete designing of business logic | Complete the task for anylysing the optimal design pattern | Complete designing of business logic | Complete the task for anylysing the optimal design pattern
|  |  | Blockers | None
| 2019-04-26 | Day 3 | Completed | Completed designing of business logic | Completed task for deciding the design pattern | Completed designing of business logic | Completed task for dewciding the desifn pattern
|  |  | Planning for next day | Analyze the requirements correctly | Analyze the Payment API requirement | Analyze the Manage order API requirement | Analyze the User Story Requirement for Add Card API
|  |  | Blockers |  | Waitng for Add card and Manage order API to be implmented
| 2019-04-27 | Day 4 | Completed | Understood the requirement | Payment API requirement | Manage Order requirement | Add card API requirement
|  |  | Planning for next day | Choose a database engine required for managing this story | Clone the Github Project Repo and create my dev branch | Designing related table for manage order API | Analyze how to create DB connection between MySql work bench and AWS RDS
Blockers
| 2019-04-28 | Day 5 | Completed | Database engine research | Cloned repo and creted my dev branch | Designed related tables in AWS RDS | Created DB connection
|  |  | Planning for next day | Analyze the process of creating database connection | Configure AWS RDS properties | API implementation to manage order | Controller class Implementation for Add Card API
Blockers
| 2019-04-29 | Day 6 | Completed | Created DB connection with AWS RDS | Configured AWS RDS properties | Created API | Created Controller class fro Add card Api
|  |  | Planning for next day | Controller class implementation for Authentication, User Profile API | Define the Payment API Interface like URI, Query Params, Request Body, Response Code, Response Body Weekly Status Report | Handle success/fail order execution | Service Class Implementation for the business logic and validation changes
Blockers
| 2019-04-30 | Day 7 | Completed | Created controller class for Login and Sign Up API | Defined the Payment API request requirement, created weekly status report | Validation of API | Created service class for Add Card
|  |  | Planning for next day | Create service class for Login and Sign Up | Define response codes and meaningful description for payment APIs error scenario | DAO class design for Order request response | DAO class to connect to AWS RDS
|  |  | Blockers |  |  | Waiting for Login and signup API to be completed for doing the registered user validation
Week #2 (14 hrs / week) | 2019-05-01 | Day 8 | Completed | Created service class for the API | Designd the different valid and invlid response | Created DAO class for API | Create DAO Class to Connect to AWS RDS
|  |  | Planning for next day | Database class creation | Design the payment API implementation which includes optimized SQL Queries to retrieve card and order details | Test edge case scenarios | Test the Flow using Post Man
Blockers
| 2019-05-02 | Day 9 | Completed | wrote required SQL Queries | Completed designing of Paymenyt API implementation | Testing edge cases | Tested the API response on Postman
|  |  | Planning for next day | Testing the requirements are satisfied using Postman tool | Implement the API i.e the controller class, service class | Add JUnit Tests | Integrate Component with other API's of Starbucks
Blockers
| 2019-05-03 | Day 10 | Completed | Unit testting | Created controller and service class | Added Junit test cses | Did integration testing woth other API
|  |  | Planning for next day | Integrate this API with the other API'S developed by other members | desing required queries in the database class | Validate emailId | Test Complete Team Portion before deploying to AWS EC2
Blockers
| 2019-05-04 | Day 11 | Completed | Integration testing with other API | wrote required SQL Queries | EmailID validation | Wrote Junit test cases
|  |  | Planning for next day | Signup Validations | write JUnit test cases for the API | Handle Null requests | Add Cards Basic Validations
Blockers
| 2019-05-05 | Day 12 | Completed | Signup Validations | wrote Junit test cases | Validation for null request | Wrote basic validation for the API
|  |  | Planning for next day | Login validations | Integrate this API with the other APIs developed by other teammates. | Start passing quantity to DB while placing order. | Add Cards Validations based on inputs from login & Sign up API
|  |  | Blockers |  | waiting other API to work successfully to test Payment API
| 2019-05-06 | Day 13 | Completed | Login validations | integration testing with other API | SQL queries | Vaildation woth other API
|  |  | Planning for next day | Making the password encrypted before storing to the database | Test end to end workflows using postman | Integrate Component with other API's of Starbucks | Write Test Cases for the Add Cards API
Blockers
| 2019-05-07 | Day 14 | Completed | Password encryption completed | Testing end to end | Integration testing with other API | wrote jUnit test cases
|  |  | Planning for next day | Deploy API to AWS as Docker Containers in Amazon Containers | Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer | Deploy API to AWS in an Auto Scaled EC2 Cluster with Load Balancer | Deploy API to AWS as Docker Containers in Amazon Containers
Blockers
Week #2 (14 hrs / week) | 2019-05-08 | Day 15 | Completed | Completed API deployment on AWS as Docker contianer | Complered deployment of API on AWS EC2 | Complered deployment of API on AWS EC2 | Completed API deployment on AWS as Docker contianer
|  |  | Planning for next day | Project Demo Presentation | Weekly Status Report | Architecture Diagram | Burndown Chart
Blockers
| 2019-05-09 | Day 16 | Completed | Completed presentation | completed weekly status report for second week | completed Diagrams | completed Burndown chart
Planning for next day
|  |  | Blockers | None

## XP Core Values
XP Core Values –
Communication – We completed the CMPE 202 Project by communicating with each other face to face daily. We have been working together on everything from requirements to code. Each of the member of our team was given an individual API to work upon. We used to meet daily to complete this project by sitting together and helping each other. We used to have a zoom call for discussion everyday in evening to keep track of what we have achieved and what is left upon. We also discussed if there’s any blocked path or is there is any bug or efficiency error in the code written. This practice helped us to handle more validations covering more edge cases in each API as it was evaluated by the different team members. This practice also helped us in learning new concepts as the members helped each other to understand new concepts on which we were not familiar before. Thus, this value of XP made our project more efficient, more understandable.
Feedback – We took every iteration commitment seriously by delivering working software according to the tasks defined for each member in the Pivotal tracker tool. Through constant feedback about our previous efforts, teams can identify areas for improvement by listening to the other member’s observation carefully and then revised their practices. This practice helped us in achieving simple design. The project also helped to gather feedback on our design and implementation in a timely manner, and then adjust our product going forward.